## Action Plan
Objective | SDAT Title | Theme | Action | Measure | Timescale (*ongoing) | RAG | Main Responsibility | Secondary Responsibility | SD Goal Supported?
1 | Governance | Communication and Engagement | Use innovative methods to promote the importance of accessible sustainable and active travel options | Run awareness activities. | 1* |  | STC |  | 11 Sustainable Cities and Communities
|  |  |  | Identify barriers and possible solutions to using active travel. | 1* |  | STC
|  |  |  | Commission new engagement display. | 1* |  | STC
1 | Governance | Contractors and Suppliers | Influence contractors and suppliers in their use and choice of sustainable transport | Continue to encourage contractors through the EMP77 Environmental Management procedure issued as part of the Control of Contractors process. | 1* |  | Estates Maintenance | SDU | 17 Partnerships for the Goals
|  |  |  | Influence suppliers via tender specifications. | 1* |  | BWPC or Finance (leases) | SDU
2 | Governance | Carbon | Assess transport and travel and calculate the carbon footprint of business travel (all road, rail and air) and patient transport. | Monitor business mileage and use SDU reporting tool to calculate footprint. | 1* |  | SDU | PAYROLL | 13 Climate Action
|  |  |  | Monitor fleet transport mileage and use SDU reporting tool to calculate footprint. | 1* |  | Vehicle owners and lease holders e.g. IM&T, Security, BCE, FM Ops | SDU
|  |  |  | Monitor community transport mileage use SDU reporting tool to calculate footprint. | 1* |  | SDU
|  |  |  | Monitor patient transport (NBT) mileage use SDU reporting tool to calculate footprint. | 1* |  | FM Ops. | SDU
2 | Governance |  | Set a local carbon reduction target for business mileage emissions. | NBT target to reduce carbon emissions is global - break down into specific areas of contribution (measurable via SDU reporting tool). | 1* |  | SDU | Managers of staff undertaking business mileage | 13 Climate Action
2 | Governance |  | Demonstrate that our carbon emissions from travel and transport are reducing in line with achieving our local target. | Monitor in relation to the above business mileage target once set. | 2* |  | SDU | PAYROLL, LEASEHOLDER AND VEHICLE OWNERS, | 13 Climate Action
1 | Governance | Business Travel | Continue to have a board approved business travel policy to support sustainable travel choices and communicate this to staff. Where business travel is unavoidable we apply a travel hierarchy, promoting active travel, public transport, car sharing and low carbon vehicles before single occupancy standard vehicles. | Obtain statistics on amounts of bus/cycle expenses claimed year on year and monitor to establish if % of business travel for these measures are increasing. | 1* |  | PAYROLL | SDU | 11 Sustainable Cities and Communities
|  |  |  | Promote travel expenses policy and travel hierarchy | 1* |  | STC | PAYROLL
|  |  |  | Define process for reimbursements of e-tickets for public transport | 1* |  | PAYROLL
3 | Governance |  | Implement senior level approval for all high carbon business travel. | Update Travel and Expenses Policy so that air travel requires senior management approval. | 3 |  | PAYROLL | SDU | 13 Climate Action
3 | Governance | Travel Plan | Continue to have a board approved healthy and active Travel Plan; developed in coordination with staff, patients, users, clients, visitors and local communities to encourage active travel. | Publish a Travel Plan and monitor effectiveness via travel surveys. | 1* |  | SDU | TRUST BOARD | 3 Good Health and Wellbeing
3 | Governance | Sustainable Travel Leads | Continue to have a lead(s) to manage sustainable travel for the organisation encompassing; business travel, fleet, logistics, private user schemes, car parking and transport services. | Continue to have STC | 1* |  | SDU |  | 12 Responsible Consumption and Production
|  |  |  | Continue to have Parking Services | 1* |  | FM Ops.
|  |  |  | Employ a Transport Manager | 2 |  | FM Ops.
1 | Governance |  | Support the sustainable travel leads with training and access to events and local/national forums for sharing best practice and innovation. | Attendance at SusCom meetings and relevant sustainable travel events/training during the year. | 1* |  | Relevant FM Managers |  | 12 Responsible Consumption and Production
2 | Governance | Improved Air Quality | Demonstrate a reduction in traffic and/or associated air quality impacts in our local area have reduced (Using the HOTT). | Using results of annual travel survey and patient travel data, run simulation using HOTT. | 1* |  | STC | SDU | 3 Good Health and Wellbeing
3 | Core Responsibilities | Business Travel | Choose locations for meetings that are accessible using public transport. | Identify key locations for any off-site meetings. | 1* |  | SDU | PAYROLL | 11 Sustainable Cities and Communities
|  |  |  | Promote locations and public transport/cycling/walking routes to meeting locations. | 2 |  | STC | SDU
3 | Core Responsibilities |  | Continue to ensure all staff using their vehicle for business mileage has appropriate and in date Drivers license and insurance (Corporate Manslaughter Act 2007). | Enforced via Travel Expenses Policy. | 1* |  | PAYROLL |  | 11 Sustainable Cities and Communities
3 | Core Responsibilities | Electric Vehicles | Implement and advertise electric vehicle charging points at all key sites which can be accessed by staff, patients and visitors. | Monitor current % of EV ownership by NBT permit holders and recommended % of available EV chargers. | 1* |  | SDU supported by STC, ESTATES and PARKING |  | 11 Sustainable Cities and Communities
|  |  |  | Implement additional EV Charging points to meet demand. | 5* |  | SDU | PARKING SERVICES
|  |  |  | Publicise existence of EV charge points on NBT sites. | 1* |  | SDU | PARKING SERVICES
|  |  |  | Explore fleet vehicle charging infrastructure requirements | 2* |  | SDU
| Core Responsibilities |  | Promote local deals on 100% electric cars to staff. | Arrange events to promote EVs and pass on promotional emails via usual Comms channels and user groups. | 1* |  | STC | Comms Team
|  |  |  | Maintain staff EV user group | 1* |  | STC
3 | Core Responsibilities |  | Ensure 10% of our fleet and pool vehicles are fully electric (Government Go Ultra Low approved vehicles or similar). | Cross reference list of electric vehicle types (Go Ultra Low) with NBT vehicle types. | 1* |  | SDU |  | 11 Sustainable Cities and Communities
|  |  |  | Explore 100% electric for existing lease arrangements. | 2 |  | SDU
3 | Core Responsibilities | Active Travel Facilities | Continue to have active travel facilities that are accessible to staff and also visitors alike. | Maintain existing facilities. | 1 |  | SDU |  | 11 Sustainable Cities and Communities
|  |  |  | Improve where/when the need arises (funding dependant) | 5 |  | SDU
|  |  |  | Investigate facilities for visitors | 5 |  | SDU | Security Services
3 | Core Responsibilities | Business Mileage | Continue to offer staff access and training for using tele and video conferencing to avoid business travel. | Ensure TravelSmart Co-ordinator is trained in how to use current facilities, produce guidance sheets on use and create a link from the intranet pages. | 1* |  | SDU | IM&T | 4 Good Quality Education
2 | Core Responsibilities |  | Undertake a business travel review to understand current patterns and proactively encourage staff to take public transport where economical and practical. | Send survey to managers of all teams who undertake business travel to understand types of business need (e.g. delivery of NBT services, meetings, training, transport etc.) and % of activity per week. | 1 |  | SDU |  | 11 Sustainable Cities and Communities
|  |  |  | Use information to feed into scoping study for centralised fleet vehicles. | 3 |  | SDU
3 | Core Responsibilities |  | Review and centralise existing pool and fleet vehicles with a minimum of 10% fully electric. | Contact all existing managers with vehicle leases. Confirm: vehicles type, fuel type, cost and length of leases, requirements for use (type of vehicle, days required, how many hours by how many staff, operational issues), current annual mileage etc. | 1 |  | SDU |  | 12 Responsible Consumption and Production
|  |  |  | Obtain quotes for replacement vehicles, telematics/online booking systems). | 2 |  | SDU
2 | Core Responsibilities |  | We segment and can report on business travel/mileage claims to assess trends on high users (e.g. directorates, departments or services) to allows us to report trends, and implement and measure actions to reduce business mileage. | Continue to monitor business mileage data and provide a break down of areas of highest use. | 1* |  | SDU | PAYROLL | 13 Climate Action
|  |  |  | Report trends via the Sustainable Development Management Plan. | 1* |  | SDU | PAYROLL
|  |  |  | Compile a list of measures which could reduce business mileage. | 2 |  | SDU
1 | Core Responsibilities | Supporting Travel Choices | Continue to support staff to make lower carbon travel choices; sharing information on cost and air pollution benefits of salary sacrifice/low carbon vehicles. | Increase or at least maintain level of uptake for Cyclescheme (monitored by Payroll) and lower-carbon travel options (monitored in T2W Survey). | 5 |  | SDU | PAYROLL | 12 Responsible Consumption and Production
|  |  |  | Use HOTT to identify health and carbon saving potential for increasing low carbon travel choices | 1* |  | SDU
3 | Core Responsibilities |  | Introduce a 'buddy' scheme for cyclists; pairing a new/less experienced cyclist with an experienced cyclist for support. | Canvas existing cyclists for interest in participating. | 1* |  | STC |  | 11 Sustainable Cities and Communities
3 | Core Responsibilities |  | Encourage and provide facilities for multi-modal journeys such as bike racks for cars. | Explore bike rack 'try before you buy' scheme and possible opportunities for discounted purchase. | 1* |  | STC |  | 11 Sustainable Cities and Communities
|  |  |  | Promote loan of Brompton bikes for people to try drive-cycle. | 1* |  | STC
3 | Core Responsibilities |  | Continue to provide information about cost savings and personal benefits or sustainable modes of commuting including personal travel planning advice and health benefits of active travel. | Maintain intranet pages with correct information. | 1* |  | STC |  | 11 Sustainable Cities and Communities
|  |  |  | Attend new starters inductions | 1* |  | STC
|  |  |  | Organise and hold engagement events at NBT sites | 1* |  | STC | SDU
|  |  |  | Collaborate with NBT Health and Wellbeing Campaigns | 1* |  | STC | NBT Health and Wellbeing Team
|  |  |  | Retain travel criteria in the Green Impact scheme | 1* |  | Green Impact Co-ordinator | STC
|  |  |  | Retain widgets on Intranet and Internet pages to encourage uptake of PTPs; identifying the travel choices patients/visitors can make. | 1* |  | STC | IM&T (internal) and Communications Team (external)
3 | Core Responsibilities | Delivery of Services | Continue to use new technologies or innovations to minimise travel in the delivery of our services. | Monitoring of available technology including its use in existing NHS settings. | 2* |  | SDU |  | 12 Responsible Consumption and Production
|  |  |  | Implementation of technology which minimises the need for travel. | 3 |  | SDU
|  |  | Continue 'supporting care closer to home', avoiding the need for travel to our services. | Use infographics to explain Sustainable Models of Care of providing care closer to home. | 1* |  | SDU |  | 11 Sustainable Cities and Communities
|  |  |  | Monitor and record the use of Sustainability Impact Assessments in business cases in relation to the reduction in travel requirements. | 1* |  | SDU
1 | Core Responsibilities | Travel Plan | Continue to have a Green Travel Plan which is communicated clearly to staff, patients, users/clients, visitors, suppliers and local communities. | Prepare 2019-2023 travel plan, consult and publicise. | 1 |  | SDU |  | 11 Sustainable Cities and Communities
|  |  |  | Maintain progress against action plan and report back to Travel Strategy Group, Sustainable Development Steering Group and include in Sustainable Development Management Plan. | 1* |  | SDU
2 | Procurement and Supply Chain | Environmental Impact Targets | Monitor the environmental impacts (CO2e and air pollution) associated with our suppliers transport and logistics and are actively work with them to find ways to minimise their traffic burden. | Identify 5 biggest suppliers and work with them to monitor mileage and impact. | 2 |  | SDU | BWPC | 13 Climate Action
2 | Procurement and Supply Chain |  | Set reduction targets for key contracts and ask tendering suppliers how they intend to reduce emissions from their associated delivery to sites. | Contact all FM suppliers to request basic logistics information e.g. vehicles used, mileage, route planning etc. | 1 |  | FM Ops. | SDU | 17 Partnerships for the Goals
|  |  |  | Set reduction targets as and when contracts are renewed. | 2* |  | SDU | FM Ops. and BWPC
2 | Procurement and Supply Chain |  | Set and monitor KPI reductions for CO2e and NOx for delivery/logistics associated with goods and services (using HOTT). | Report emissions identified from key contracts. | 2* |  | SDU |  | 17 Partnerships for the Goals
2 | Procurement and Supply Chain | Fleet, Pool Cars and Transport | We will assess which option is most sustainable when procuring our own pool cars, fleet vehicles and/or logistic and transport solutions (i.e. measuring the CO2e, PM2.5 impacts of each option/vehicle type). | Use Sustainability Impact Assessments to determine the most sustainable option. | 1* |  | All staff procuring vehicles | SDU | 13 Climate Action
3 | Procurement and Supply Chain |  | Introduce a minimum specification for procured vehicles (Euro 4 for Petrol and Euro 6 for Diesel). | Introduce a specification for all leases, contracts and purchases which stipulates a minimum requirement for Euro 4 Petrol and Euro 6 Diesel. | 2 |  | BWPC | SDU | 12 Responsible Consumption and Production
|  |  |  | Check all Sustainability Impact Assessments in business cases for vehicle purchases to ensure the correct specification has been stated. | 2 |  | SDU
1 | Procurement and Supply Chain | Local Travel and Infrastructure | Continue to collaborate closely with stakeholders to support local area improvements of travel services and infrastructure (including local authorities, public transport and taxi services, university and local businesses). | Continue to attend external meetings with stakeholders and partners (i.e.. North Bristol Suscom, local authorities and transport providers) and participate in local campaigns and surveys. | 1* |  | SDU |  | 11 Sustainable Cities and Communities
2 | Working with Staff, Patients and Communities | Monitoring | Continue to monitor travel choices for visitors, patients, users and clients and promote active travel and the use of public transport. | Collect travel data through Patient travel survey techniques. | 1* |  | STC | Business Intelligence Team | 11 Sustainable Cities and Communities
2 | Working with Staff, Patients and Communities |  | Continue to participate in an annual staff travel survey to measure shifts in modes of transport and make an action plan for reducing the environmental, social and financial impacts of travel. | Promote and encourage participation in the annual TravelWest Travel to Work Survey. | 1* |  | STC | Communications Team | 11 Sustainable Cities and Communities
|  |  |  | Use Travel to Work Survey results as a base for Travel Plan and associated Action Plan. | 2* |  | SDU
1 | Working with Staff, Patients and Communities | Supporting Travel Choices | Continue to encourage staff with training and incentives to uptake and increase active travel (e.g. Cyclescheme, bike loans and cycle mileage rates *competitive with driving rates*). | Provide access to a cycle to work scheme (bike purchase scheme) and loan bikes. | 1* |  | SDU |  | 11 Sustainable Cities and Communities
|  |  |  | Adopt and promote a cycle mileage rate that is competitive with that for car drivers and considers longer distances achievable by electric bicycles. | 3 |  | PAYROLL | SDU
1 | Working with Staff, Patients and Communities |  | Participate in national awareness days to encourage staff to walk and run for their commute and throughout their daily routines. | Run events and participate in national awareness campaigns. | 1* |  | STC |  | 11 Sustainable Cities and Communities
3 | Working with Staff, Patients and Communities |  | Allocate increased priority parking for car sharers as/when demand increases. | Monitor levels of car share usage through car share parking permits and Travel to Work survey. | 1* |  | Parking Services and STC |  | 11 Sustainable Cities and Communities
|  |  |  | Creation of car share bays in convenient locations across the Trust to incentivise car sharing. | 3 |  | Parking Services and SDU
1 | Working with Staff, Patients and Communities |  | Continue to provide information through TravelSmart, encouraging multi-modal travel options as flexible and expected ways to commute. | Maintain TravelSmart inbox; responding to queries. | 1* |  | STC |  | 11 Sustainable Cities and Communities
|  |  |  | Continue to provide a Brompton loan bike scheme for park/bus/train and ride. | 1* |  | STC
|  |  |  | Investigate the option of providing a bicycle rack loan scheme for staff to try park and cycle. | 2 |  | STC
1 | Working with Staff, Patients and Communities |  | Continue to provide information to patients, users and clients on how to avoid using a car when accessing the Trusts sites. | Continue to offer personal travel plans. | 1* |  | STC |  | 11 Sustainable Cities and Communities
|  |  |  | The Trust ensures information about travelling to site prioritises sustainable travel before car use. (e.g. site access leaflets, external website.) | 1* |  | Communications Team | SDU
|  |  |  | Ensuring the Trust sites have the necessary infrastructure to allow access using sustainable modes of transport. | 1* |  | Sustainable Health and Capital Planning, Estates Maintenance and Bouygues | SDU
|  |  |  | Continue to lobby transport providers, local authorities and other external stakeholders for improvements to services and infrastructure which supports sustainable travel to our sites. | 1* |  | SDU
3 | Working with Staff, Patients and Communities |  | Establish a motorcycle buddy scheme for new riders; pairing experienced with less experienced riders. | Canvas existing motorcyclists for interest in participating. | 2* |  | STC |  | 11 Sustainable Cities and Communities
|  |  |  | If interest is high enough, pair new riders with more experienced ones. | 2* |  | STC
1 | Working with Staff, Patients and Communities |  | Continue to discourage solo occupancy staff commute journeys. | Continue to maintain the Travel to Work Zones (Parking Policy) to discourage unnecessary vehicle travel. | 1* |  | Parking Services |  | 11 Sustainable Cities and Communities
|  |  |  | Continue to provide the TravelSmart travel advice bureau service. | 1* |  | STC
1 | Working with Staff, Patients and Communities | Collaborative Improvements | Continue to work with partners and stakeholders to assist with improvement of local air quality (i.e. develop plans to reduce traffic impacts, support infrastructure for active travel and promote the use of public transport and active travel). | Continue to attend external meetings (i.e.. North Bristol Suscom, local authorities) and participate in local, regional and national campaigns and surveys. | 1* |  | SDU |  | 11 Sustainable Cities and Communities
3 | Working with Staff, Patients and Communities | Business Travel | Continue to provide pool cars for business travel. | Pool cars are provided and use is monitored and reported on at the end of the annum. | 1* |  | SDU |  | 11 Sustainable Cities and Communities
3 | Working with Staff, Patients and Communities |  | Investigate the replacement of current pool car arrangement with leased vehicles to improve efficiency and cost of Trust business journeys. | Investigation is undertaken with end report identifying improvements. | 2* |  | SDU |  | 11
1 | Working with Staff, Patients and Communities | Social Prescribing | Increase the prescribing of walking and cycling as alternatives or to compliment other interventions. | Clinicians are using the LWNB map and other materials to prescribe active travel to patients who would benefit | 1* |  | All clinicians at the Trust | SDU | 11 Sustainable Cities and Communities
|  |  |  | Promote the use of LWNB maps with local health and wellbeing providers. | 1* |  | SDU
1 | Working with Staff, Patients and Communities | Health and Wellbeing | Continue to promote active travel as beneficial for health and wellbeing. | Collaborate with NBT Health and Wellbeing in campaigns and events throughout the travel plan lifespan (Aiming for a minimum 1 event per annum). | 1* |  | SDU | NBT Health and Wellbeing | 17 Partnerships for the Goals

## Goal Descriptions
Goal | Description
1 | Engage with staff, patients, visitors, local community, suppliers, partners and other stakeholders on sustainable travel and the health co-benefits; persuading them to convert to more sustainable modes of transport.
2 | Monitor and report on the environmental and health impacts from emissions and air quality from travel/transport to our site to assess the effects and opportunities for improvements.
3 | Provide information, facilities, processes and infrastructure to facilitate and incentivise sustainable and active travel.

## SD Goal Descriptions
Number | Title | Brief | Relevant Goal/s
3 | Good Health and Well-Being | Ensuring healthy lives and promoting the well-being at all ages. | By 2030, reduce by one third premature mortality from non-communicable diseases through prevention and treatment and promote mental health and well-being. By 2020, halve the number of global deaths and injuries from road traffic accidents.
4 | Good Quality Education | Obtaining a quality education is the foundation to creating sustainable development. In addition to improving quality of life, access to inclusive education can help equip locals with the tools required to develop innovative solutions to the world’s greatest problems. | ???? By 2030, substantially increase the number of youth and adults who have relevant skills, including technical and vocational skills, for employment, decent jobs and entrepreneurship
11 | Sustainable Cities and Communities | Future in which cities provide opportunities for all. Efficent urban planning and management practicies are in place to deal with challenges of urbanisation (congestion, lack of funds, declining infrastructure, air pollution). | By 2030, provide access to safe, affordable, accessible and sustainable transport systems for all, improving road safety, notably by expanding public transport, with special attention to the needs of those in vulnerable situations, women, children, persons with disabilities and older persons
12 | Responsible Consumption and Production | Promoting resource and energy efficency, sustainable infrastructure and providing access to basic services, green jobs and better qaulity of life for all. Reduce resource use, degradation and pollution along the whole life cycle while increasing quality of life. | By 2030, achieve the sustainable management and efficient use of natural resources. Encourage companies, especially large and transnational companies, to adopt sustainable practices and to integrate sustainability information into their reporting cycle. By 2030, ensure that people everywhere have the relevant information and awareness for sustainable development and lifestyles in harmony with nature. Support developing countries to strengthen their scientific and technological capacity to move towards more sustainable patterns of consumption and production.
13 | Climate Action | Climate change effects every country and is disrupting lives, communities and people. Affordable, scaleable solutions are available to enable cleaner, more resilent economies. | Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries. Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning
17 | Partnerships for the Goals | Successful sustainable development requires partnerships built upon principles and values, shared visions and shared goals that place people and planet at in the centre. Local, national, regional, global. Review and monitoring frameworks must be done to reinforce sustainable development. | Enhance policy coherence for sustainable development. ?????
9 | Industries, Innovation and Infrastructure | Growth in productivity and incomes, and improvements in health and education outcomes require investment in infrastructure. Technological progress is the foundation of efforts to achieve environmental objectives, such as increased resource and energy-efficiency. | By 2030, upgrade infrastructure and retrofit industries to make them sustainable, with increased resource-use efficiency and greater adoption of clean and environmentally sound technologies and industrial processes, with all countries taking action in accordance with their respective capabilities. Develop quality, reliable, sustainable and resilient infrastructure, including regional and transborder infrastructure, to support economic development and human well-being, with a focus on affordable and equitable access for all.